## Sheet1
Critical | Day | 1 | Day | 2 | Day | 3 | Day | 4 | Day | 5 | Day | 6 | Day | 7 | Day | 8 | Day | 9 | Day | 10 | Day | 11 | Day | 12 | Day | 13 | Day | 14 | Day | 15 | Day | 16 | Day | 17 | Day | 18 | Day | 19 | Day | 20
Non-critical
Project manager | Custommer meting/research |  | 1 | PM
Designer A | Color palette |  |  |  | 1 | DA
Photographer A |  |  |  |  | 1 | PA
Photographer B | Meeting and planning(photo) |  |  |  | 1 | PB
Author A | Casual content tezt |  |  |  | 1 | AA | 1
Author B | About crew and company text |  |  |  | 1 | AB | 1
Designer A | [6 empty] | 0.5 | DA
Designer B | Sketching | [5 empty] | 0.5 | DB
Photographer A | Nature photoshoot | [6 empty] | PA | 1 | 0.5
¦
Photographer B | Fruit and product photoshoot | [6 empty] | PB | 1 | 0.5
Project manager | Answering emails | [6 empty] | PM | 1
Photographer B | Person/crew photoshoot | [9 empty] | 1 | PA
Project manager | Making presentation | [9 empty] | 1 | PM
Designer A | [10 empty] | 1 | DA
Designer B | Styile tile | [9 empty] | 1 | DB
Front End A | HTML Sketching | [9 empty] | 1 | FEA
Project manager | Meeting | [11 empty] | 1 | PM
Designer A | [14 empty] | 1 | DA
Designer B | Correction/changing(design) | [13 empty] | 1 | DB
Photographer A | [14 empty] | 1 | PA
Photographer B | Possible new shoot | [13 empty] | 1 | PB
Author A | [14 empty] | 1 | AA
Author B | Content correction | [13 empty] | 1 | AB
Front End A | HTML | [15 empty] | 1 | FEA
Front End A | CSS | [17 empty] | 1 | FEA | 1 |  | 1
Project Manager | Answeing mails | [17 empty] | 1 | PM
Project Manager | [20 empty] | 1 | PM
Designer A | [20 empty] | 1 | DA
Designer B | [20 empty] | 1 | DB
Author A | WEB PAGE TESTING(Internally) | [19 empty] | 1 | AB
Author B | [20 empty] | 1 | AA
Photographer A | [20 empty] | 1 | PA
Photographer B | [20 empty] | 1 | PB
Project Manager | [24 empty] | 1 | PM
Designer A | [24 empty] | 1 | DA
Designer B | [24 empty] | 1 | DB
Author A | [24 empty] | 1 | AA
Author B | Public 1 day testing | [23 empty] | 1 | AB
Photographer A | [24 empty] | 1 | PA
Photographer B | [24 empty] | 1 | PB
Front End A | [24 empty] | 1 | FEA
Author A | [26 empty] | 1 | AA
Author B | Correcting | [25 empty] | 1 | AB
Front End A | [26 empty] | 1 | FEA
Project Manager | Meeting | [27 empty] | 1 | PM
Author A | [30 empty] | 1 | AA
Author B | Correction | [29 empty] | 1 | AB
Front End A | [30 empty] | 1 | FEA
Designer A | [32 empty] | 1 | DA
1
Designse B | Finalizing | [31 empty] | 1 | DB
Front End A | [32 empty] | 1 | FEA
Project manager | [34 empty] | 1 | PM
Front end | Launch | [33 empty] | 1 | FEA
Persons: |  |  | 1 |  | 5 |  | 3 |  | 3 |  | 5 |  | 1 |  | 6 |  | 1 |  | 2 |  | 8 |  | 1 |  | 8 |  | 3 |  | 1 |  | 3 |  | 4 |  | 2
Number:
Total work days: |  | Price if 1000kf a day |  |  |  | Total hours spent on project | [5 empty] | Days between start to finnish
57 |  | 57000 |  |  |  | 1368 | [5 empty] | 18

## Ark1
Critical | Day | 1 | Day | 2 | Day | 3 | Day | 4 | Day | 5 | Day | 6 | Day | 7 | Day | 8 | Day | 9 | Day | 10 | Day | 11 | Day | 12 | Day | 13 | Day | 14 | Day | 15 | Day | 16 | Day | 17 | Day | 18 | Day | 19 | Day | 20
Non-critical
Tasks-->
Persons
Project manager | Customer meeting/research |  |  |  |  | Answering emails |  |  | Making presentation |  | Meeting |  |  |  |  | Answeing emails | [10 empty] | Meeting
Designer Alpha |  |  | Color palette
Designer Bravo |  |  |  |  | Sketching |  |  |  | Style tile |  |  |  | Corrections/changes |  |  |  | Internal web page testing
Internally and externally
testing
Photographer Alpha |  |  | Meeting and planning |  |  | Nature photoshoot
Photographer Charlie | [5 empty] | Fruit and product photoshoot | [6 empty] | Possible new shoot |  |  |  | Internal web page testing
Photographer Bravo | [7 empty] | Person/crew photoshoot
Front-end Alpha | [8 empty] | HTML Sketching | [6 empty] | HTML-bone | CSS | [7 empty] | Coerrection
Author Alpha |  |  |  | Casual content text | [8 empty] | Content correction | [11 empty] | Correction
Author Bravo |  |  |  | About crew and company text | [8 empty] | Content correction |  |  |  | Internal web page testing